## Weekly Plan
10-Week Plan — Inventory SaaS + System Design + DSA
Edit only the yellow Status column. Progress updates automatically. Green row = version 1 live; start applying for jobs at the end of week 4.
Progress | 0 of 10 weeks done | 0%
Week | Build | System design topic | DSA pattern | Friday mock | Status | Notes
1 | Docker setup, CI, NestJS basics, auth with sessions | Client-server, HTTP, REST, monolith vs. microservices | Arrays, hash maps | — | Not started
2 | Orgs, roles, products, barcodes, Arabic/English | SQL vs. NoSQL, indexes, normalization, pagination | Two pointers, sliding window | URL shortener | Not started
3 | Stock movements, audit log, safe sale | ACID, transactions, isolation levels, locking | Stacks, binary search | — | Not started
4 | Dashboard, deploy, logs — VERSION 1 LIVE | Caching, load balancers, logging | Trees, BFS/DFS | Rate limiter | Not started
5 | CSV import with a queue | Message queues, async jobs, retries, idempotency | Heaps | — | Not started
6 | Multiple warehouses, transfers | Data modeling, consistency, ledger pattern | Graphs | E-commerce checkout | Not started
7 | Low-stock alerts | Scheduled jobs, notifications, rate limiting | Intervals, greedy | — | Not started
8 | Stripe plans | Webhooks, third-party integrations, eventual consistency | Backtracking | Notification system | Not started
9 | AI invoice scanning | Object storage, timeouts, fallbacks | Dynamic programming basics | — | Not started
10 | Load test, monitoring, ARCHITECTURE.md, landing page | Horizontal scaling, replication, sharding, CAP theorem | Review | Design your own inventory system | Not started

## Daily Routine
Daily Routine (about 6.5 hours)
Every Friday: one classic system design question on paper for 45 minutes, then compare with a reference answer.
Block | Minutes | What
DSA | 45 | 1–2 problems, no AI
Learn | 60 | This week's system design topic
Build | 240 | Apply it in the inventory SaaS; write the hard parts by hand
Explain | 30 | Write it in LEARNING.md in your own words
Total hours | 6.25

## First 3 Days
What to do in the first 3 days
Test for every week: explain your whole setup to someone without notes.
Day | Do | Learn | Status
Day 1 | Install Docker. Create the repo. Run Postgres and Redis with docker-compose up. Read the NestJS overview docs. | What HTTP and REST are | Not started
Day 2 | Create a NestJS app with one products module (controller, service). Add a GitHub Actions file that runs lint and tests. | Monolith vs. microservices; why a modular monolith | Not started
Day 3 | Connect Postgres with Drizzle and write your first migration. Start auth: sign up, log in, sessions. | How sessions and cookies work | Not started

## Resources
Resources (keep it to these)
If you already finished some system design topics, skim those weeks faster — don't restart from zero.
Area | Resource | How to use it
System design | System Design Primer (GitHub, free) | Concepts for each week's topic
System design | ByteByteGo | Visual explanations
System design | Designing Data-Intensive Applications, chapter 7 | Transactions — read in week 3
DSA | NeetCode 150 | Filter to this week's pattern
NestJS | Official docs: Overview + Fundamentals | Week 1 foundation